AGILE PROJECT MANAGEMENT METHODS FOR IT PROJECTS

The difference between failure and success is the difference between doing something almost right and doing something right.	-Benjamin Franklin

Agile project management methodologies used to develop, deploy, or acquire information technology systems have begun to enter the vocabulary of modern organizations. Much in the same way lightweight and agile manufacturing or business management processes have over the past few years. This chapter is about applying Agile methods in an environment that may be more familiar with high ceremony project management methods – methods that might be considered heavy weight in terms of today’s agile vocabulary.

High ceremony projects include projects based on formal or semi– formal project management methods, ones like Prince2 [1], PMI’s PMBOK [2], or processes based on the Software Engineering Institute’s Capability Maturity Model [3]. These methods are traditionally associated with organizations that operate in software engineering centric business domains. These domains view software activities as an engineering process, rather than a creative process based in the skill of individuals or small teams. Organizations with mature processes often define their activities in a formal manner, applying methods with rigor, and monitoring the processes and results carefully. These practices are many times built up over time and come about through direct experiences – either good or bad. Many times, they follow the formal structure of the underlying business process.

It is common to talk about Agile methods for modern project management processes in the context of a set of lightweight activities used to manage the development or acquisition of software. These activities include   requirements,  design,   coding,  and   testing   processes   based  on   a minimal set of activities needed to reach the end goal —  a working software system. [4]

[1] Projects IN Controlled Environments (PRINCE) is a structured project management method used in the United

Kingdom.

[2] Project Management Body of Knowledge (PMBOK) is an ANSI Standard PMI– 99– 001–2000 describing the

various attributes of a project management method.

[3] Capability Maturity Model is a collection of model frameworks for assessing the maturity of a specific practice.

Key Practice Areas are used to define the various levels of maturity. CMM now consists of: Software, People,

Software Acquisition, Systems Engineering, and Integrated Product Development. This models are supported

by a software process assessment standard ISO/IEC 15504.

Although some of these agile development methods address the management aspects of software projects – people, processes, and technology –  they are primarily focused on coding, testing, and software artifact delivery. [5]

Applying the concept of agility to the management of a software project is a natural step in the evolution of software development. One important question to be asked though is how these minimalist approaches can be applied to traditional project management activities?

[4] SCRUM, DSDM, Crystal, Adaptive Software Development, and Extreme Programming.

[5] Some proponents of these lightweight methods contend delivery of software is the only goal.   Although this is

an  obvious outcome of the programming and integration process, there are  many other deliverable artifacts

associated with large– scale software projects.

- What project management process simplifications are appropriate for a specific problem domain? [6]

- Are all lightweight and agile project management process steps applicable to specific problem domains? If not which steps are applicable to which domains?

Weight versus Agility

In the information technology project management literature, lightweight is often defined as not heavyweight, which is a tautology. Over time lightweight has been superceded in the trade press and literature by the term Agile. Lightweight and Agile are not interchangeable words however. This distinction is not well understood by many agile proponents, so some clarification is needed here before we proceed. Lightweight describes the weightiness of the process and its artifacts. The amount of potentially non– value added artifacts produced by a specific process. This weightiness can be attributed to the undesirable consequences of the process –  artifacts that don’t provide benefit to the out-come. This weightiness can also be attributed to the mis-application of a specific process. Agility describes the behavior of the participants and their ability to move or adjust in new and possibly unforeseen situations.

Much   like   an   overweight   boat,   airplane   or   athlete,   the   undesirable weight needs to be removed in order to increase the efficiency of the vehicle. This is a standard best practice in many engineering disciplines. One problem with this analogy though is that anyone suggesting a specific methodology is over weight must answer the question:

…   if   a  project   management   method   were   properly applied,   in the   proper     domain,   to   the  proper set   of  problems,  with  properly   trained  participants,     would    it be   considered   overweight    and   produce   undesirable   consequences?

The usual answer is no, of course not. If everyone were doing their job properly, in the proper engineering, regulatory, and contractual environment, then the results would be accepted by all the participants – this is the definition of a tautology.

The   problem   of Agile   project   management   methodology   selection   is compounded by the behaviors of the method as well as the behaviors of the participants using the method. In addition, the appropriateness of the method for a specific problem domain remains an issue. Making a process lightweight by removing activities or artifacts is most likely in-appropriate and a possible source for project failure without careful consideration of the consequences.

Project Management Framework

According to the Software Engineering Institute, a methodology must posses certain attributes in order to meet the requirements of being called a methodology.  Another framework for methodologies is the Software   Engineering   Body   of   Knowledge   (SWEBOK)   that   contains other knowledge development methods to be used by any professional software engineer. For the moment, we’ll focus on the SEI’s description of the software project attributes. Figure 1 describes how these attributes could be related in an  agile  project management method. This structure is a process pattern view of project activities. This approach focuses on the communication and people– centric aspects of project management. Agile project management can be built on this framework.

Milestones

Tools

Techniques

Activities

Quality

Products

Standards

Development

Environment

Skills

Roles

Teams

Management

Methods

People

Management

Processes

Work

Environment

The Agile Software Delivery Process

Agile   processes   emphasize   both   the   rapid   and   flexible   adaptation   to changes   in   the   process,   the   product,   and   the   development   environment [7]. This is a very general definition and therefore not very useful without some specific context.

Before   establishing   this   context, Agile   processes   include   three   major attributes, they are:

- Incremental and Evolutionary –  allowing adaptation to both internal and external events.

- Modular and Lean –  allowing components of the process to come  and go depending on specific needs if the participants and stakeholders.

Time Based –  built on iterative and concurrent work cycles, which      contain feedback loops and progress checkpoints.

[7] “New Age of Software Development: How Component Based Software Engineering Changes the Way of

Software Development,” Mikio Aoyama, 1998 International Workshop on Competent– Based Software

Engineering, 1998.

Common Problems with All Software Projects

The National Software Quality Experiment has been conducted each year since 1992 with the following observations reoccurring over the years:

| Common Problem | Consequences |
| --- | --- |
| Software product source code components are not traced to requirements | Software product is not under the control and the verification procedures are imprecise. Changes can not be managed in a controlled manner. |
| Software engineering practices are not applied in a systematic manner. | Defect rates are unacceptable. |
| Product designs and source are managed in an ad hoc manner | The understandability, maintainability, and adaptability of the product are negatively impacted. |
| The construction processes for the product are not clearly defined. | Common patterns of t he processes are not exploited. |
| Rapidly c hanging code base has become the norm. | The code base services the only the short term benefits and mortgage s the future where traceable baseline requirements, specifications, and design artifacts are the foundations of success. |

The Problem of Change

Change continually takes place in the business   world, at all levels within an organization or market place. Change by itself is not the problem. The world is always changing. It always has been changing. It always will be changing. Businesses and the processes they use have always had to adapt to this changing world. Often changes in the past have occurred incrementally. When a radical change took place, the next change event was slow in coming. While there has always been uncertainty in business, it was usually not significant or sustained.

The problem in today’s world is that change is no longer incremental or even linear. Radical non– linear changes occur in the normal course of business. The pace of change is not only increasing, sustained uncertainty is now commonplace.

Ready For Agility?

All organizations face problems that can be addressed by Agile methods, but not all companies are ready for the radical ideas needed to become an Agile organization. Agility is still an emerging topic and is at the stage where it is not possible to buy an off– the– shelf solution that has been shown to behave in the same manner as heavier weight processes. Elements of agility can certainly be found in many processes, but as the saying goes – one swallow does not a make summer.

The introduction of an Agile process should only be undertaken by organizations that are risk aware if not risk adverse. Organizations who need answers and concepts that are fully developed that result in a solution that can be implemented with little risk should stay clear of the Agile Processes. The irony is though – there is no such process that can deliver a fully developed plan that result in a fully developed project or product.

Let alone one that can be deployed without risk.

The Forces Driving Agility

Software acquisition and deployment is generally driven by a need to solve a specific problem, to do things better, to modify or improve a business or technical process. The software development process community has two schools of thought regarding the outcome of these efforts:

- Things are getting better

- Things are getting worse

This conflicting set of opinions adds more confusion to an already confusing question of — are we actually improving the outcome of the software by improving the management processes?

A few years ago, methodologies and processes were the domain of academics. The methodology zoo has grown however and at the same time become focused on the commercial aspects of selling these methodologies to anxious managers, developers, and stakeholders. This selling process has, in many cases, overtaken the rational application of these methods of specific problem domains.

Practical Agile Project Management

The deployment of an Agile project management methodology in an existing organization faces several obstacles:

- The   legacy   project   management   processes   must   be   displaced   in some way to make room for the new process.

- The gaps that existed in the legacy process must be filled with the new process while maintaining the integrity provided by the legacy process.

Common Threads of These Methods

In an attempt to simplify the many attributes of the methods, a list of common threads can be built, using Figure 1 as a framework.

Is Agile Yet Another Software Methodology Taxonomy?

Before selecting a software development method, some understanding of what type of software is to be developed is appropriate. By partitioning software system into types, the appropriateness question can be addressed —  what   project   management   methods   are   appropriate   for   what problem domains?

Framework for Agile Project Management Methods A framework for deploying Agile project management processes provides a descriptive   guideline   rather   than  a   proscriptive   set   of   rules.   This framework approach provides the user a broader set of recommendations than is found in any particular named methodology. This framework is based on two foundations:

01. The Software Program Managers Network Nine Best Practices. Which provides guidelines for project managers

using practical suggestions for daily application.

02. Scott Ambler’s Agile Modeling framework –  which provides a broad  framework for creating agile   processes

applied   to   software   projects.

Agile Project Management Guidelines

Building on the Software Program Managers Nine Best Practices, the well established project management methods of the past, the fundamentals of any project management method, and finally common sense, a framework for Agile Project Management can be built.

Values of Agile Project Management

Before the principles of Agile Project Management can be defined, a set of underlying values are useful.

- Communication – of information within and outside an Agile project is constant. It is the responsibility of the project manager to ensure that the communication occurs effectively, clearly, and in a timely manner between the management, the contributors, and the stakeholders. Since change is constant in an Agile project, constant communication is the only means of maintaining the connections between all the participants. Going Dark for any significant amount of time is simply not allowed.

- Simplicity – defines the approach to identifying the critical success      factors of the project in terms of the simplest possible solution. All activities must contribute a measurable value to the project management process. Measuring the value of a project management artifact is the role of the stakeholders and the project manager. This is done by asking what is the value of this specific task, artifact, or project deliverable?

- Feedback – “optimism is an occupational hazard of software development, feedback is the cure”. Continuous feedback is a primary tool for defining and sustaining Agility.

- Courage – all important decisions and changes in the direction of  the project need to be made with the courage. Change is part of any realistic IT project. Dealing with the consequences of change or discarding the outcome when the decision is proven inadequate requires courage.

- Humility – the best project   managers   acknowledge   they   don’t know everything. The stakeholders, project participants, and customers all have their area of expertise and add value to the project. An effective approach is to assume that everyone involved with the project has equal value and therefore should be treated with respect.

Applying Agile Principles in Practice

Applying these principles in practice creates the foundation for managing IT projects in an Agile manner.

- Assume Simplicity – as the project evolves it should be assumed that the simplest solution is the best solution.  Overbuilding the system or any artifact of the project must be avoided. The project manager should have the courage to not perform a task or produce an artifact that is not clearly stated in the requirements as needed for the immediate benefit of the stakeholders.

- Embrace Change –  since requirements evolve over time. The stake holder understanding of the requirements will change over time. Project stakeholders themselves may change as the project makes progress. Project   stakeholders   may   change   their   point   of   view,   which in turn will change the goals and success criteria of the project management effort.

- Enabling The Next Effort Is Also A Goal –  the project can still be considered a failure even when the team delivers a working system to the users. Part of fulfilling the needs of the project stakeholders is to ensure that the system is robust enough to be extended over time. Using Alistair Cockburn concept, “when you are playing  the software development game your secondary goal is to setup to play the next game.” The next phase may be the development of a major release of the system or it may simply be the operation and support of the current version of the system.

- Incremental Change –  the pressure to get it right the first time can overwhelm the best project manager. Instead of futilely trying to develop an all encompassing project plan from the start, put a stake in the ground by developing a small portion of the system, or even a high– level model of a larger portion of the system, and evolves this portion over me. Or simply discard it when you no longer need it in an incremental manner.

- Maximize Stakeholder Value – the project stakeholders are investing resources, time, money, facilities,... to have a system deployed that meets their needs. Stakeholders expect that their in-vestment to be applied in the best way.

- Manage With A Purpose – create artifacts of the project manage-ment process that have stakeholder value. Identify why and for whom the artifact is created. Identify a valid purpose for creating the artifact and the audience for that artifact. This principle also applies to a change to an existing artifacts.

- Multiple Project Views – provide different views of the same process for different audiences. Considering the complexity of any modern information technology system construction or acquisition process, there is a need for a wide range of presentation formats in order to effectively communicate with the stakeholders, participants, and providers.

- Rapid Feedback – the time between an action and the feedback on that action must be minimized. Work closely with the stake-holders, to understand the requirements, to analyze those require-ments, and develop a actionable plan, which provides numerous opportunities for feedback.

- Working Software Is The Primary Goal of the Project – the goal of any software project is to produce software that meets the needs of the project stakeholders. The goal is not to produce extraneous documentation, management artifacts, or even models of these arti-facts. Any activity that does not directly contribute to the goal of producing a working system should be examined.

- Travel Light – every artifact that is created, and kept, will need to be maintained over it’s life cycle. The effort needed to maintain these artifacts must be balanced with their value. Not only must the effort be considered, but the risk that the artifact will create confusion over time if it is not properly maintained must be con-sidered.

# Recommendations to Practitioners

- Make incremental change to the requirements, project plan system, and the resulting artifacts to enable agility.

- Strive for rapid feedback to ensure the project meets the needs of all the participants and stakeholder.

- Manage with a purpose, performing only those tasks that add value to business processes supported by the system.

- Travel light, discarding processes and artifacts that don’t add enduring value to the product a working software system.